## Sheet1
Wk # | Week | Task | Responsibility
1 | 2016-02-08 | Finish and Submit Proposal | Team
|  | Research R.F. Transmitter and Receiver Modules | Eric
|  | Research Optical Adjustment Techniques/Theory | Noah
2 | 2016-02-15 | Research Laser Transmitter and Photodetector Modules | Team
|  | Research MCUs and Power Module | Team
|  | Develop encryption algorithm and communication protocol | Noah
3 | 2016-02-22 | Develop circuit for photodetector and R.F. Modules | Eric
|  | Select and Buy Parts/Sensors | Team
|  | Finalize Design Review Documentation | Team
4 | 2016-02-29 | Finish and Submit Design Review + Presentation | Team
|  | Construct basic laser transmission circuit with protoboard | Noah
|  | Construct basic R.F. circuit with protoboard | Eric
5 | 2016-03-07 | Establish communication between both Laser Transmitter and Photodetector | Team
|  | Establish communication between R.F Transmitter and R.F. Receiver | Eric
|  | Implement PWM with laser | Team
6 | 2016-03-14 | Implement RF Encryption Algorithms on MCU | Noah
|  | Test and Debug | Team
|  | Finalize Construction before Spring Break | Team
7 | 2016-03-21 | Spring Break (NO SCHOOL) | ----
8 | 2016-03-28 | Assemble Friendly Interrogator System | Noah
|  | Assemble Friendly Target System | Eric
|  | Test and Debug | Team
9 | 2016-04-04 | System Integration Tests | Team
|  | Test Tolerance Analysis | Team
|  | Revisions for PCB | Team
10 | 2016-04-11 | Sign up for Presentations | Team
|  | Final Revision PCB | Team
|  | Field Test and Verify Requirements Met | Team
11 | 2016-04-18 | Test System Integration | Team
|  | Finalize Construction | Team
|  | Prepare Presentation and Demonstration | Team
12 | 2016-04-25 | Friendly Interrogator System Documentation | Noah
|  | Friendly Target System Documentation | Eric
|  | Finish Final Report/Documentation | Team
13 | 2016-05-02 | Prepare Presentation | Team
|  | Final Report/Presentation | Team
|  | Check-in Supplies | Team